# Team Pipeline & Plan

Digital Platform for Farmer Procurement Registration, Slot Booking & Status Tracking — SIH Problem ID 26032

This document is for you, the team lead. It explains, in plain language, how the whole project will be built from day one to demo day, how the work is split across 6 people, and how the 6 pieces connect into one working app. Each teammate also gets their own separate, very simple, step-by-step document — hand those out after you've read this one.

# 1. The Big Picture — What We're Building

A mobile-first web app (works like an app but opens from a link, so no app-store delay) where a farmer can register, book a slot to sell grain, get notified, walk through the centre, get their grain quality-checked, and get paid — while tracking every step on their phone. There is also an admin screen for the procurement centre staff.

We are building 6 pieces ("modules"). Each piece is small enough for one person to own start to finish, but all 6 pieces talk to one shared database so the app feels like one product, not six.

# 2. Decisions Already Made (so nobody has to guess)

The working draft left some choices open for the team. Here are the defaults chosen so everyone can start building today. Your team can change any of these together, but don't build against a different stack on your own — it will break integration.

| Decision | Choice |
| --- | --- |
| MVP scope | Build the 5 officially required pieces first (registration, slot booking, notifications, queue/capacity, payment status). Assaying (quality check) is a bonus 6th module — build it if time allows, but it is not what gets you disqualified if late. |
| Frontend | React (a JavaScript framework) styled with Tailwind CSS, built as a PWA (Progressive Web App) — one shared frontend project, one folder per module. |
| Backend | Node.js with Express (a JavaScript backend framework) — one shared backend project, one folder of routes per module. |
| Database | MongoDB (a flexible, easy-to-learn database) using Mongoose to define the data shapes. |
| Data source | Mocked data for land records, mandi capacity, and bank verification — NOT real government APIs. This is a hackathon; fake but realistic data is expected. |
| Real-time behaviour | Not true real-time. The app re-checks for updates every 30 seconds to a couple of minutes (called "polling"). This is simpler to build and works better on poor rural networks than always-on connections. |
| Code hosting | One shared GitHub repository, one branch per person, merged into 'main' regularly. |
| API testing tool | Postman (a free tool to test backend routes without needing the frontend finished). |

# 3. The 6 Modules (1 module = 1 person)

These come straight from the working draft's "Core Modules" list. Assign one to each teammate.

| # | Module Name | One-line job |
| --- | --- | --- |
| 1 | Registration & Verification | Let a farmer sign up and get their identity/land record checked (or flagged for manual review). |
| 2 | Slot Booking & Rescheduling | Let a farmer pick a date/time to bring their grain, and reschedule if they miss it. |
| 3 | Notification Service | Tell farmers what's happening via SMS + a phone-call fallback + in-app messages. |
| 4 | Capacity Sync & Admin Console | Give centre staff a screen to update warehouse space, labour, bag stock, truck schedule — and stop overbooking. |
| 5 | Assaying / Quality Check (bonus) | Record the grain quality test result against a farmer's booking, including partial acceptance. |
| 6 | Payment Status Tracker | Show the farmer real, live status of their payment instead of a black box. |

💡 Modules 1, 2, 4 and 6 are the backbone — they touch the official 5 deliverables directly. If someone finishes early, they help Module 5 (bonus) or Module 3 (notifications), since those depend on the others being ready first.

# 4. How the 6 Modules Talk to Each Other

Every module reads and writes to a shared database using 7 shared 'shapes' of data (called schemas/collections). Nobody needs to memorise all of them — each teammate's own document only shows the shapes THEY need. Here is the map for you as team lead:

| Data shape | Owned (written) by | Also read by |
| --- | --- | --- |
| Farmer | Module 1 (Registration) | Modules 2, 3, 6 |
| Slot | Module 4 (Capacity Sync) | Module 2 |
| Booking | Module 2 (Slot Booking) | Modules 3, 4, 5, 6 |
| Centre | Module 4 (Capacity Sync) | Module 2 |
| AssayRecord | Module 5 (Assaying) | Module 6 |
| Payment | Module 6 (Payment Tracker) | Module 3 |
| Notification Log | Module 3 (Notifications) | Admin console (Module 4) |

In plain words: Module 1 creates the farmer. Module 4 creates the available slots. Module 2 links a farmer to a slot (that's a "booking"). Modules 3, 5 and 6 all react to a booking existing — they don't create bookings, they add information on top of one.

# 5. Order of Work — Who Waits for Whom

Nobody can build 100% blind to the others — but the dependency order below tells you who needs a small 'starter version' from someone else before they can properly test.

- Day 1 (everyone, together): Team lead creates the GitHub repo, the empty React app, the empty Express app, and the MongoDB database. Everyone installs their tools (see each person's document, Section 2) and clones the repo. Agree on the exact data shapes in Section 4 above — do not change field names later without telling everyone.

- Days 2–4 (everyone, in parallel): Each person builds their own module against FAKE/dummy data first — nobody needs to wait. Module 1 (Registration) and Module 4 (Capacity Sync) should aim to finish a basic working version first, since Modules 2, 3, 5, 6 all depend on Farmer and Slot data existing.

- Day 5: First integration checkpoint. Module 2 (Slot Booking) connects to real data from Module 1 and Module 4 instead of fake data. This is the moment 'one farmer books one real slot' becomes possible end-to-end.

- Days 6–7: Modules 3, 5, 6 connect to real Bookings from Module 2 instead of fake data. Now notifications, quality checks, and payment status all react to real bookings.

- Day 8: Full integration test — one person walks through the ENTIRE farmer journey (register → book → get notified → get assayed → get paid) and everyone fixes whatever breaks.

- Day 9–10: Polish (loading states, error messages, mobile screen sizes), rehearse the demo, prepare slides/pitch.

💡 Adjust the day numbers to however many days/weeks you actually have — the ORDER (setup → build in parallel against fake data → connect Module 2 first → connect the rest → integrate → polish) stays the same whether it's a 10-day sprint or a 4-week build.

# 6. Team Process (keep it light)

- Daily 10-minute stand-up: each person says what they built yesterday, what they're building today, what's blocking them.

- Everyone pushes their code to their own branch at least once a day, and opens a Pull Request into 'main' — even if it's not finished. Small, frequent merges beat one giant merge at the end.

- Nobody edits another person's module folder without a quick message first.

- If two people need to change a shared data shape (Section 4), that's a team decision, not a solo one — it affects everyone.

# 7. What You Hand Each Teammate

Give each person ONLY their own module document (not this whole pipeline doc, unless you want them to see the big picture too — recommended for at least a quick skim). Each module document is self-contained: it explains, in very simple steps, what to install, what the module does, exactly what data fields to build, the order to build things in, how to test it alone, and how it connects to everyone else.

| Document | Give to |
| --- | --- |
| Module 1 — Registration & Verification | Teammate A |
| Module 2 — Slot Booking & Rescheduling | Teammate B |
| Module 3 — Notification Service | Teammate C |
| Module 4 — Capacity Sync & Admin Console | Teammate D |
| Module 5 — Assaying / Quality Check | Teammate E |
| Module 6 — Payment Status Tracker | Teammate F |